## Test Plan
S No | Test Name | Description | C Part | SV Part
1 | SOC_RST_001 | [P0] Power-on reset held for multiple clocks, released synchronously; repeat reset. Check reset values, no spurious AXI/WB requests, peripherals quiescent, reset polarity and release latency. | N/A (reset-only test; core held in reset or idle). | Reset sequence (rst_n driver); passive AXI/WB monitors; reset-value checks; assertions: no VALID after reset, outputs idle.
2 | SOC_RST_002 | [P1] Assert reset during idle, during a peripheral transfer and during an outstanding external memory request. No stale response/IRQ; clean recovery; document unsupported in-flight abort behaviour. | Optional: C routine that starts a peripheral transfer and then re-checks register defaults after reset. | Virtual sequence: start traffic then pulse reset at chosen phase; scoreboard flush; post-reset 'no phantom response' assertion; reset-phase coverage.
3 | CORE_BOOT_001 | [P0] Boot initialised minimal program from configured reset vector (0xEE000000 in ICCM); perform arithmetic and signature store. Needs functional VeeR config. | Minimal C/startup (crt0 + main): arithmetic, store signature word to agreed address in Data RAM (0x06000000). | Preload ICCM/DCCM hex image; release reset; AXI slave memory agent; compare signature/retirement; check no unexpected trap.
4 | CORE_MEM_001 | [P0] Instruction fetch plus aligned byte/halfword/word loads/stores supported by configuration via LSU adapter. Check data, strobes, sign/zero extension, ordering, IFU/LSU routing. | C test with volatile loads/stores of every width (lb/lbu/lh/lhu/lw/sw) to known RAM addresses; self-check values. | AXI monitor on LSU 64-to-32 adapter; scoreboard with byte-addressed reference memory and WSTRB checks.
5 | CORE_EXC_001 | [P1] Illegal instruction, misalignment, access fault and privilege/PMP cases enabled by configuration. Check trap cause/PC/status and return. | C test with trap handler: trigger each exception, read mcause/mepc/mtval, return via mret; report to signature. | Checker comparing expected trap cause/PC from signature/trace; coverage on exception classes.
6 | CORE_IRQ_001 | [P1] Pulse and hold selected peripheral interrupt lines; software enables/clears interrupt. Core takes expected interrupt and returns; no lost/duplicate event. | C ISR + PIC/CSR (mie/mstatus) enable; count interrupts into signature; clear peripheral source flag. | Interrupt agent drives peripheral IRQ lines (pulse/level); check ISR count matches events.
7 | CORE_DBG_001 | [P2] JTAG TAP reset/IDCODE and halt/resume/register access if debug build is enabled. | Optional: simple C loop/counter to observe halt/resume. | JTAG agent: TAP reset, IDCODE read, halt/resume/register access sequences; TAP response checker.
8 | LOCAL_MEM_001 | [P0] Exercise ICCM/DCCM initialised and uninitialised regions, boundary and configured size. Correct local data/fetch, no unintended alias, configuration-specific protection. | C test walking first/last words of ICCM and DCCM, pattern write/read-back, check alias offsets. | Memory-config object (sizes/bases); scoreboard reference storage; boundary/alias checks.
9 | XBAR_DECODE_001 | [P0] Single reads/writes to each implemented target window (m00..m11) and unmapped/reserved windows. Correct target select; no cross-target leakage; expected DECERR for unmapped region. | C probe of each peripheral base/last address (volatile access); record bus-error/trap for unmapped windows. | AXI master agent single transfers per window; target monitors confirm single-target select; response (OKAY/DECERR) checker; decode coverage.
10 | XBAR_ARB_001 | [P0] VeeR LSU (s00) and DMA master (s02) issue simultaneous requests to same and different targets. Arbitration as specified, no starvation, independent target progress. | C code triggering DMA memory transfer while executing concurrent memory read/write loops. | Two active AXI master monitors with synchronised start (virtual sequence); arbitration/starvation scoreboard.
11 | XBAR_CHAN_001 | [P0] AW and W arrive independently in either order; concurrent read and write. Channel independence, no response before acceptance, matching ID/response. | N/A (needs pin-level channel control). | AXI master sequence with randomised AW/W order and delays; ID/response matching scoreboard; channel-order assertions.
12 | XBAR_BURST_001 | [P1] INCR bursts with legal lengths (4, 8, 16 beats), sizes, lane alignment and boundary cases to RAM targets. Beat count, address progression, WLAST/RLAST, ID preservation. | Optional: C memcpy/memset-style loops or DMA burst config to trigger bursts. | AXI burst sequences (len/size/boundary constraints); WLAST/RLAST checkers; address-progression scoreboard.
13 | XBAR_STALL_001 | [P1] Random target READY delays and master response backpressure. Payload stability, no loss/duplication, eventual completion. | N/A. | Random ready/valid delay config in master and slave agents; stability assertions; transaction count scoreboard.
14 | XBAR_ERR_001 | [P1] Inject SLVERR/DECERR from target and unmapped access while traffic is in flight. Interconnect resilience, correct master routing, no crossbar lockup. | C test accessing unmapped window with bus-error handler. | Target error-injection sequence; response router checker; interconnect recovery assertions.
15 | XBAR_STRESS_001 | [P2] Constrained-random concurrent traffic from multiple initiators (CPU s00, Spare s01, DMA s02) to mixed targets with randomised wait-states. | C workload running continuous peripheral polling loops. | Multi-master virtual sequence; crossbar transaction scoreboard; performance/latency monitors; starvation checks.
16 | WB_BRIDGE_001 | [P0] AXI-Lite reads/writes to each mapped Wishbone register (addr[3:2]); correct cyc/stb/we/sel assertion and ack_o termination. | C register read/write to I2C registers via bridge. | AXI master sequence; Wishbone slave protocol monitor; timing/handshake assertions.
17 | WB_BRIDGE_WAIT_001 | [P1] Insert Wishbone ACK delay and supported error/stall conditions. Bridge handles wait-states without dropping AXI requests. | C driver performing standard I2C read/write. | Wishbone agent delaying ack_o; AXI handshake stability checker; timeout assertions.
18 | WB_BRIDGE_RESET_001 | [P1] Reset during Wishbone idle and active cycle. Wishbone controls idle immediately; AXI slave resets cleanly. | N/A. | Reset pulse during cyc/stb active; Wishbone signal deassertion assertions; post-reset recovery check.
19 | I2C_REG_001 | [P0] Program prescaler (PRER_LO, PRER_HI), control (CTR), TX/RX registers; read back defaults; byte strobes and core enable. | C register read/write test via AXI-to-WB bridge. | AXI-Lite register sequence; I2C register model and field checks.
20 | I2C_WRITE_001 | [P0] Master START, address + write bytes, slave ACK, STOP. Open-drain line behaviour, bit order, SCL frequency, ACK sampling, completion/IRQ. | C I2C driver: set prescaler, enable core, TXR, CR=START¦WRITE, poll status TIP==0, issue STOP. | I2C slave agent/monitor (ACK model); open-drain checks; SCL frequency/bit-order scoreboard.
21 | I2C_READ_001 | [P1] Address + read bytes, ACK intermediate byte and NACK final byte, STOP. Received bytes, ACK/NACK sequencing, status and IRQ. | C driver reading multi-byte data, setting ACK/NACK in command register, reading RXR. | I2C slave agent returns data; scoreboard compares RXR; ACK/NACK sequencing checker.
22 | I2C_NACK_001 | [P1] NACK address and data phases. Arbitration/status flags (RxACK=1), transaction termination and software-visible status. | C driver checking RxACK status after NACK and issuing STOP. | I2C slave agent NACK injection; status checker; no bus deadlock assertion.
23 | I2C_STRETCH_001 | [P1] Slave holds SCL low during transfer. Clock stretching honoured and transaction resumes without data corruption. | C driver performing normal transfer (no firmware modification needed). | I2C slave agent stretches SCL; check master waits; data integrity scoreboard.
24 | I2C_RESTART_001 | [P1] Repeated START and multi-byte command sequences without bus release. Correct bus sequence and command engine status. | C driver issuing repeated START (write register address, then read data) sequence. | I2C monitor checks repeated START condition; bus-sequence scoreboard.
25 | I2C_ARB_001 | [P2] Competing master pulls SDA low during a released-high bit. Arbitration loss detection (AL=1) and bus release if implemented. | C driver checking arbitration-lost status bit in SR. | I2C agent as competing master; arbitration-loss and bus-release checks.
26 | I2C_RESET_STRESS_001 | [P2] Reset at multiple bus phases and random timing stress. Safe line release to high-Z, no phantom completion, protocol scoreboard clean. | N/A. | Random reset injection at bus phases; open-drain line-release assertions; protocol scoreboard.
27 | AES_REG_001 | [P0] Reset defaults, write/read key registers (KEY0..KEY3) and plaintext input registers (TEXT0..TEXT3); status flags (DONE, KDONE). | C register read/write test: populate KEY and TEXT registers, verify readback. | AXI-Lite register sequence; AES register model; access permission checks.
28 | AES_KAT_001 | [P0] FIPS-197 AES-128 known-answer encryption vector. Ciphertext matches expected standard vector; latency and DONE/KDONE flags correct. | C driver: load NIST 128-bit key, load NIST plaintext, trigger KLD¦LD in CTRL, poll DONE==1, read OUT0..OUT3, self-check. | AXI monitor capturing key/plaintext/ciphertext; reference C/DPI AES model scoreboard; latency checker.
29 | AES_RELOAD_001 | [P1] Re-key and run multiple plaintexts; randomised keys/data. Verify no state leakage between successive operations. | C loop with changing keys and multiple data blocks; verify each block against expected signature. | Randomised stimulus sequence; continuous AES scoreboard; round-state independence assertions.
30 | AES_BUSY_001 | [P1] Access/control writes while operation is active (DONE=0). Defined ignore/stall behaviour; no corrupted output. | C test attempting writes to KEY/TEXT registers during active encryption polling loop. | Concurrent write sequence during active rounds; corruption checker; output comparison against golden model.
31 | AES_RESET_001 | [P1] Synchronous reset (RST=1) during idle and active operation. Status/output registers return to clean reset state; subsequent operations succeed. | C routine asserting soft reset mid-cipher, then re-initializing and verifying fresh encryption. | Reset injection during cipher rounds; state machine idle assertion; post-reset functional check.
32 | AES_STRESS_001 | [P2] Random legal programming, polling and response stalls. Throughput, scoreboard clean, no hang. | C stress loop executing continuous encryption under heavy system load. | AXI ready backpressure; randomised transaction intervals; high-volume ciphertext scoreboard.
33 | UART_REG_001 | [P0] Read/write implemented registers; reset defaults; DLAB/divisor switching, LCR, IER, and LSR status bits. | C register test: verify reset defaults, write/read LCR, IER, set DLAB=1, write/read baud divisor, clear DLAB. | AXI-Lite register sequence; UART register model; DLAB-switching assertions.
34 | UART_TXRX_001 | [P0] Configure common frame (8N1), transmit known bytes, receive and verify deserialization at standard baud rate. | C driver configuring 8N1, writing THR, polling LSR for TX empty, reading RBR for RX byte. | UART agent monitor on uart_tx_o and driver on uart_rx_i; frame-timing scoreboard; data match check.
35 | UART_LOOP_001 | [P0] Internal/external loopback (TX tied to RX) and back-to-back bytes. No loss, correct ordering, character integrity. | C loopback test: transmit sequence of test bytes (e.g. 0x55, 'START'), poll RX ready, read and verify identical bytes. | Loopback connection model; character-order and byte-latency scoreboard.
36 | UART_FIFO_001 | [P1] Empty/full/threshold, FIFO clear, bursts, simultaneous TX and RX. Watermark and status flags (THRE, TEMT, DR). | C routine pushing burst to THR, checking FIFO full flag, draining RX FIFO. | Burst stimulus agent; FIFO level/watermark assertions; overrun protection checks.
37 | UART_FMT_001 | [P1] Supported word lengths (5, 6, 7, 8 bits), parity modes (none, even, odd, stick), stop-bit settings (1, 2 bits). Frame format matches spec. | C test programming each LCR format setting, sending test characters, verifying readback masks. | UART agent verifying serial frame formatting (start, data width, parity, stop bits); format covergroup.
38 | UART_ERR_001 | [P1] Parity, framing, break, overrun and noise injection on RX pin. LSR error bits assert correctly and clear on read. | C test reading LSR error flags after fault injection, verifying PE/FE/OE bits, reading RBR to clear. | UART agent error-injection sequences (bad parity, early stop bit zero, buffer overflow); error-status checker.
39 | UART_IRQ_001 | [P1] Enable/disable RX Data Ready, TX Empty, line-status interrupts in IER. Interrupt asserts to PIC; clears on servicing. | C ISR for UART interrupt: read LSR to identify cause, read RBR or reload THR, verify IRQ deasserts. | Interrupt monitor observing uart_irq; assertion/deassertion timing checker; PIC routing check.
40 | UART_STRESS_001 | [P2] Random serial timing within tolerance (+/- 2% baud jitter) plus concurrent system memory traffic. Frame decoder resilience. | Continuous C console print loop while running background RAM tests. | UART agent with randomised bit-period jitter; framing resilience scoreboard; character loss assertion.
41 | SPI_REG_001 | [P0] Soft reset via SPI_SRR (0x0A); verify reset defaults in SPI_CR, SPI_SR (TX_EMPTY=1, RX_EMPTY=1), and SPI_SSR. | C test: write 0x0A to SPI_SRR, read back SPI_SR and SPI_CR, verify core disabled and FIFOs empty. | AXI-Lite register sequence; SPI register model; soft-reset assertions (FIFOs flushed, CS high).
42 | SPI_TXRX_001 | [P0] Full-duplex 8-bit SPI byte exchange. Core drives MOSI; external slave drives MISO; verify simultaneous bidirectional transfer. | C driver: enable master mode, assert CS0 (SPI_SSR=0xFFFFFFFE), write SPI_DTR=0xA5, poll TX_EMPTY, read SPI_DRR. | SPI slave agent detects CS0 low, samples MOSI on active SCLK edges, shifts MISO=0x5A; scoreboard checks DTR/DRR match.
43 | SPI_MODES_001 | [P1] All 4 SPI operational modes (Mode 0: 00, Mode 1: 01, Mode 2: 10, Mode 3: 11) via CPOL and CPHA in SPI_CR. Clock idle levels and sampling phase. | C driver looping through all 4 CPOL/CPHA combinations, executing byte exchange for each. | SPI agent dynamically adapting clock polarity and edge sampling; protocol checker checks SCLK idle state and MOSI/MISO timing.
44 | SPI_CLK_DIV_001 | [P1] Clock prescaler sweep via SPI_RCLK (divisors 2, 4, 8, 16, 32). SCLK frequency scaling, 50% duty cycle, setup/hold margins at max speed. | C driver programming SPI_RCLK with each divisor value, transmitting test byte, verifying completion. | SPI monitor measuring SCLK cycle period; SVA asserting T_sclk == Divisor * T_core_clk; duty cycle checker.
45 | SPI_SLAVE_SEL_001 | [P1] Multi-slave select addressing via SPI_SSR (CS0..CS3). Verify active-low drive on targeted slave line and high-Z/inactive on unaddressed lines. | C driver sequentially selecting each slave line (0..3), transmitting unique token byte, deasserting CS. | Multi-slave SPI VIP monitoring all CS lines; asserts strictly one slave active at a time; checks CS setup/hold times.
46 | SPI_FIFO_001 | [P1] Continuous multi-byte burst transmission by loading TX FIFO; verify back-to-back shifting with CS held low continuously. | C routine writing 8 consecutive bytes to SPI_DTR, polling TX_EMPTY, reading 8 received bytes from SPI_DRR. | SPI VIP verifying continuous SCLK shifting with zero inter-byte gaps; FIFO ordering and watermark assertions.
47 | SPI_STRESS_001 | [P2] Randomized payload transfer at maximum clock speed (divisor 2) with back-to-back slave responses and random CS delays. | C stress loop transmitting random byte blocks over SPI while core runs concurrent arithmetic. | Randomised SPI slave agent; high-speed protocol scoreboard; setup/hold violation checkers.
48 | GPIO_REG_001 | [P0] Read/write direction register (DIR); verify reset default (0x00000000 = all inputs); shadow register readback. | C test reading default DIR, programming alternating input/output masks (0x0000FFFF, 0xFFFF0000), verifying readback. | AXI-Lite register sequence; GPIO register model; tri-state buffer direction assertions on gpio_io[31:0].
49 | GPIO_OUT_001 | [P0] Drive test patterns (walking 1s, walking 0s, 0x55555555, 0xDEADBEEF) to DATA_O; GPIO agent monitors gpio_io[31:0] pins. | C driver setting all pins as outputs (DIR=0xFFFFFFFF), writing test patterns to DATA_O. | GPIO VIP capturing physical levels on gpio_io[31:0]; real-time pin level scoreboard against DATA_O.
50 | GPIO_IN_001 | [P0] GPIO agent drives 32-bit test vectors on input pins; C reads DATA_I; verify 100% data integrity and synchronizer operation. | C driver configuring all pins as inputs (DIR=0x00000000), reading DATA_I across 10 iterations, storing to RAM. | GPIO VIP driving randomized 32-bit vectors onto gpio_io pins; scoreboard comparing driven levels to DATA_I readback.
51 | GPIO_ATOMIC_001 | [P1] Atomic single-instruction bit manipulation: SET_O, CLR_O, and TGL_O registers without read-modify-write races. | C driver initializing DATA_O=0x00000000, issuing SET_O, CLR_O, and TGL_O writes, verifying result in DATA_O. | GPIO VIP monitoring cycle-by-cycle pin transitions; assertions verifying only targeted bits toggle and untargeted bits remain stable.
52 | GPIO_IRQ_EDGE_001 | [P1] Edge-triggered interrupt generation (rising and falling edge) on gpio_irq; verify ISR execution and W1C status clear. | C ISR for GPIO: enable edge IRQ on pin 8, clear status via INT_STS (W1C), record serviced event. | GPIO agent driving rising/falling transitions on gpio_io[8]; interrupt monitor checking gpio_irq assertion and deassertion.
53 | GPIO_IRQ_LVL_001 | [P1] Level-sensitive interrupt generation (high level and low level); verify interrupt persistence until pin deasserts. | C driver configuring level interrupt, masking in INT_EN to exit ISR. | GPIO agent holding pin high/low; interrupt monitor checking continuous gpio_irq assertion.
54 | GPIO_STRESS_001 | [P2] High-frequency pin toggling and rapid direction switching while generating concurrent interrupts. | C loop rapidly toggling output pins while monitoring input status. | GPIO VIP capturing high-frequency transitions; race condition and glitch checkers.
55 | TIMER_REG_001 | [P0] Read/write prescaler (PRE), initial load (LOAD), and control (CTRL) registers; reset defaults; counter enable/disable. | C register read/write test: program PRE, LOAD, read live counter VAL. | AXI-Lite register sequence; Timer register model; counter increment/decrement assertions.
56 | TIMER_ONESHOT_001 | [P0] One-shot counting mode: timer counts to target, asserts timer_irq, and halts without rolling over. | C driver setting CTRL[1]=0 (one-shot), loading count, enabling timer, waiting for IRQ, reading VAL at halt. | Timer VIP monitoring timer_irq; SVA checking counter halts at terminal count and does not restart.
57 | TIMER_PERIODIC_001 | [P0] Periodic auto-reload mode: continuous tick generation; verify zero cumulative drift across 10+ reload periods. | C ISR counting 10 consecutive timer expiration interrupts, measuring elapsed software cycles. | Timer VIP measuring interval between consecutive timer_irq pulses; asserts period == LOAD * (PRE + 1) cycles.
58 | TIMER_PWM_001 | [P0] PWM generation on pwm_o using Compare Register (CMP); measure period and duty cycle (minimum, 25%, 50%, 75%, maximum). | C driver programming LOAD and CMP thresholds, enabling PWM mode in CTRL. | Timer VIP measuring high-time and low-time on pwm_o; waveform scoreboard verifying duty cycle matches CMP/LOAD ratio.
59 | TIMER_PWM_UPDATE_001 | [P1] Dynamic duty cycle update during active period; verify glitch-free transition on pwm_o pin. | C driver modifying CMP register mid-run without stopping counter. | Waveform monitor checking output transitions smoothly without runt pulses or illegal state glitches.
60 | TIMER_CAPTURE_001 | [P1] Input capture mode: external edge on capture_i latches live counter snapshot into CAP register and triggers IRQ. | C ISR reading CAP register after capture interrupt, validating captured count. | Timer agent injecting pulse on capture_i at cycle T; scoreboard checking CAP register == counter(T).
61 | TIMER_STRESS_001 | [P2] Random prescaler and compare values over extended periods; cross-coverage of period x duty cycle. | C loop cycling through random legal prescaler and compare settings. | Randomised configuration sequence; PWM waveform scoreboard; period x duty cross coverage.
62 | DMA_REG_001 | [P0] Read/write source (SRC), destination (DST), length (LEN), config (CFG), and control (CTRL); verify reset defaults. | C register test: read default status (BUSY=0, DONE=0), write/read descriptor registers. | AXI-Lite register sequence on slave port m11; DMA register model; master port s02 idle assertions.
63 | DMA_MEM2MEM_001 | [P0] Autonomous 64-byte burst copy from Program RAM (0x0500_0000) to Data RAM (0x0600_0000); verify DONE status and data match. | C driver: populate Program RAM buffer, zero Data RAM, set DMA_SRC/DST/LEN, trigger GO=1, poll DONE==1, verify buffer match. | Interconnect monitor on port s02 checking AR/R read burst from Prog RAM and AW/W write burst to Data RAM; memory copy scoreboard.
64 | DMA_REVERSE_001 | [P1] Reverse transfer: 128-byte copy from Data RAM to Program RAM; verify multi-beat burst splitting across boundary. | C driver: set DMA_SRC=Data RAM, DMA_DST=Prog RAM, DMA_LEN=128, trigger DMA, verify destination buffer. | AXI master monitor checking multi-burst splitting (INCR length 16 beats); WSTRB=0xF assertions; data integrity check.
65 | DMA_UNALIGN_001 | [P1] Non-word-aligned transfers (e.g. source offset +1 byte, destination offset +3 bytes); verify byte-lane steering and partial strobes. | C driver setting unaligned source and destination pointers, verifying individual memory bytes after transfer. | AXI monitor verifying narrow transfers and WSTRB lane masking; scoreboard checking unaligned byte copy.
66 | DMA_IRQ_001 | [P1] Transfer completion interrupt: verify dma_done signal asserts PIC interrupt line; verify CPU ISR handling. | C ISR for DMA: enable DMA IRQ in PIC, put CPU in WFI, service ISR upon completion, clear status. | Interrupt monitor observing dma_done pulse; assertion verifying interrupt arrives upon final write response (BVALID & BREADY).
67 | DMA_ERR_001 | [P1] Error response handling: configure unmapped address as DMA source; verify DECERR detection, dma_error flag, and bus release. | C driver pointing DMA_SRC to unmapped window (0xF0000000), triggering transfer, checking ERROR status bit in DMA_STAT. | Interconnect returns DECERR; SVA checking DMA terminates cleanly without locking master port s02; dma_error flag asserted.
68 | DMA_STRESS_001 | [P2] Continuous ping-pong DMA transfers between memories while CPU generates concurrent peripheral traffic. | C firmware running UART/AES operations while DMA streams background memory buffers. | Multi-master interconnect scoreboard; bus contention checkers; zero memory corruption assertion.
69 | RAM_PROG_RW_001 | [P0] Full-word and multi-word read/write access to Program RAM (0x0500_0000); verify OKAY response and data integrity. | C word write/read loops across Program RAM address space; pattern comparison. | AXI slave monitor on port m05; reference memory scoreboard; OKAY response checker.
70 | RAM_DATA_RW_001 | [P0] Full-word and multi-word read/write access to Data RAM (0x0600_0000); verify memory isolation from Program RAM. | C word write/read loops across Data RAM; verify no cross-talk into Program RAM. | AXI slave monitor on port m06; reference memory scoreboard; address decode isolation check.
71 | RAM_STRB_001 | [P0] Byte-lane write strobes (wstrb) for 8-bit, 16-bit, and 24-bit writes; verify unmasked bytes preserved. | C byte and halfword store instructions (sb, sh) to test memory; verify unaffected bytes retain original data. | Strobe-mask sequence (all 16 wstrb combinations); lane-preservation scoreboard.
72 | RAM_BURST_001 | [P1] AXI INCR burst writes and reads (lengths 4, 8, 16); verify consecutive address progression and zero wait-states. | Optional: C block copy or DMA burst trigger. | AXI burst sequences; WLAST/RLAST checkers; address-progression scoreboard.
73 | DUMMY_SLAVE_001 | [P0] Write and readback verification to Dummy Slaves 0-3 (0x0700_0000, 0x0800_0000, 0x0900_0000, 0x0A00_0000); verify bus decoding. | C test writing unique values (0x07, 0x08, 0x09, 0x0A) to each dummy slave base, reading back and verifying. | AXI monitors on ports m07..m10; target select and readback scoreboard.
74 | SOC_MISSION_001 | [P0] Boot software configures UART, SPI, I2C, GPIO, runs AES KAT, triggers DMA copy, reports final status via UART. End-to-end SoC verification. | Full C firmware: uart_init, aes_encrypt, spi_exchange, gpio_drive, i2c_start, dma_copy, uart_puts('ALL TESTS PASSED'). | Full SoC UVM virtual sequence: preload hex, release reset; monitor all peripheral pins; end-to-end scoreboard; zero protocol errors.

## Notes
Source: Secure-IoT-Gateway-SoC UVM Verification Test Plan, comprehensive IP and SoC verification matrix (74 tests).
Test Name = standardized test ID. Priority ([P0] / [P1] / [P2]) is indicated at the beginning of each Description.
ASSUMPTION - C Part: embedded C firmware executed on the VeeR EL2 core (or C/DPI-C reference code) for the test. 'N/A' = test requires pin-level or protocol control that software cannot directly drive.
ASSUMPTION - SV Part: SystemVerilog/UVM sequences, protocol VIP agents (UART, SPI, I2C, GPIO, Timer, DMA, AXI), scoreboards, assertions (SVA), and functional coverage.
The C Part / SV Part separation provides clear division of responsibility between software test sequences and hardware verification components for HW/SW co-verification.
Peripherals covered: VeeR EL2 Core, AXI Interconnect 3x12, AXI-to-WB Bridge, I2C Master, AES-128 Core, UART Controller, SPI Master, GPIO Controller, General Timer & PWM, DMA Engine, Program & Data RAMs, Dummy Slaves, and PIC Interrupts.